## Test Case
ID | Title | Precondition | Steps | Test Data | Expected Result | Actual Result | Status | Priority | Related User Story
TC01 | Register with valid data | User is on registration screen | 1. Open the app 2. Navigate to registration 3. Fill all required fields with valid data 4. Submit the form | Email: ahmed.maher.tester@gmail.com Password: Test@1234 Birthdate: optional | New account is created and user is redirected to dashboard | The user successfully registers and is redirected to the dashboard | pass | High | User Registration
TC02 | Register with short password | User is on registration screen | 1. Fill form with password < 8 characters 2. Submit | Password: 1234567 | Error message: 'Password must be at least 8 characters' | User is registered and logged in | Fail | High | User Registration
TC03 | Register with existing email | Email already exists in system | 1. Enter existing email 2. Fill valid data 3. Submit | Email: ahmed.maher.tester@gmail.com | Error message: 'Email already exists' | Account created successfully without error | Fail | Medium | User Registration
TC04 | Register without birthdate | User is on registration screen | 1. Fill all required fields 2. Leave birthdate blank 3. Submit | Birthdate: — | Registration successful, redirected to dashboard | Form shows validation error: "Birthdate required" | Fail | Low | User Registration
TC05 | Auto login after registration | User has just completed registration | 1. Complete registration 2. Observe behavior |  | App auto logs in and redirects to dashboard | User is automatically logged in and redirected to dashboard after registration | pass | Medium | User Registration
TC06 | Registration page loads correctly | App is opened | 1. Navigate to registration screen |  | Registration form with all fields appears | Registration form with all fields loads properly | pass | Low | User Registration
TC07 | Password field hides characters | User is on registration screen | 1. Focus on password field 2. Start typing |  | Characters should be hidden (••••) | Characters appear as plain text | Fail | Low | User Registration
TC08 | Login with valid credentials | User is on login screen | 1. Enter valid email and password 2. Submit login form | Email: ahmed.maher.tester@gmail.com Password: Test@1234 | User is logged in and redirected to dashboard | User is logged in and redirected to dashboard | pass | High | User Login
TC09 | Login with invalid credentials | User is on login screen | 1. Enter wrong email or password 2. Submit login form | Email: ahmed.ahmed@gmail.com Password: wrongpass | Error message: 'Invalid credentials' | App shows error message “Invalid credentials | pass | High | User Login
TC10 | Login with empty fields | User is on login screen | 1. Leave fields empty 2. Submit login form |  | Validation errors for required fields | Validation errors shown for both fields | pass | Medium | User Login
TC11 | Login with Google | User is on login screen | 1. Click on 'Login with Google' 2. Complete OAuth flow |  | User logged in via Google and redirected to dashboard | App shows a blank screen after successful authentication | Fail | Medium | Login with Google
TC12 | Login with Apple | User is on login screen | 1. Click on 'Login with Apple' 2. Complete Apple Sign-in flow |  | User logged in via Apple and redirected to dashboard | Apple login flow completed successfully and user redirected to dashboard | Pass | Medium | Login with Apple
TC13 | Create one-time task with valid data | User is logged in and on dashboard | 1. Click create task 2. Choose one-time task 3. Enter title and date 4. Submit | Title: Dentist Date: 2025-07-15 | Task is saved and shown on dashboard | Task “Dentist” saved and shown correctly on dashboard | Pass | High | Create a New One Time Task
TC14 | Create one-time task without title | User is on task creation screen | 1. Go to create task 2. Leave title blank 3. Enter date and submit | Date: 2025-07-15 | Validation error: 'Title is required' | App crashes after clicking submit | Pass | High | Create a New One Time Task
TC15 | Create one-time task with description | User is on task creation screen | 1. Enter title, date, and optional description 2. Submit | Title: Call Bank Date: 2025-07-10 Description: Follow up | Task is saved and shown on dashboard | Task with title and description created successfully and visible on dashboard | Pass | Medium | Create a New One Time Task
TC16 | Create weekly task for 4 weeks | User is logged in and on dashboard | 1. Click create task 2. Choose repeatable > weekly 3. Enter title and 4 weeks 4. Submit | Title: Gym Repeat: 4 weeks | Task is saved and appears as weekly | Weekly task created successfully, displayed with correct repeat info | Pass | High | Create a New Weekly Task
TC17 | Create weekly task with no repeat number | User is on task creation screen | 1. Enter title only 2. Leave repeat blank 3. Submit | Title: Reading | Validation error: 'Repeat duration is required' | App shows error “Repeat duration is required | Pass | Medium | Create a New Weekly Task
TC18 | Create monthly task for 6 months | User is logged in and on dashboard | 1. Click create task 2. Choose repeatable > monthly 3. Enter title and months 4. Submit | Title: Pay Rent Repeat: 6 months | Task saved and appears monthly | Monthly task created and displayed with correct repeat duration | Pass | High | Create a New Monthly Task
TC19 | Change account name | User is logged in | 1. Navigate to settings 2. Edit name field 3. Save changes | New Name: Ahmed M. | Name updated across the platform | Named is updated successfully | Pass | Low | Change Account Name
TC20 | Change password with correct current password | User is logged in | 1. Go to settings 2. Enter current, new, and confirm password 3. Save | Current: Test@1234 New: Test@5678 | Password updated successfully | Password Updated Successfully | Pass | High | Change Account Password
TC21 | Change password with wrong current password | User is logged in | 1. Enter wrong current password 2. Try to save | Current: wrongpass | Error: 'Current password incorrect' | Password Updated Successfully | Fail | High | Change Account Password
TC22 | Create public task | User is logged in | 1. Go to task creation 2. Set visibility to public 3. Enter details and save | Title: Community Cleanup | Task visible to all users | Public task is not visible in User B's dashboard or public section | Fail | Medium | Add Public Task
TC23 | Like a public task | User is viewing public task | 1. Click like button |  | Like count increases by 1 | Like count increased by 1 and reflected immediately | Pass | Low | Like Public Task
TC24 | Comment on public task | User is logged in and on task details | 1. Type comment 2. Click post | Comment: Great job! | Comment displayed with username and time stamp | Comment posted and displayed with username and time stamp | Pass | Medium | Comment on Public Task
TC25 | Follow another user | User is logged in | 1. Visit user profile 2. Click follow |  | User now followed, activities appear in feed | User followed successfully, activities started appearing in feed | Pass | Low | Follow Other Users
TC26 | Switch language to Arabic | App is in English | 1. Go to settings 2. Change language to Arabic |  | App interface changes to Arabic | Some screens still display text in English | Fail | Low | Change App Language from English to Arabic
TC27 | Switch language to English | App is in Arabic | 1. Go to settings 2. Change language to English |  | App interface changes to English | App interface switched back to English | Pass | Low | Change App Language from Arabic to English
TC28 | Try to create task without selection task | User is on task creation screen | 1.Click New Task 2.Do not select task type 3.Click next or try to proceed |  | App should display an error “please select a task type” | Nothing happens, and user is stuck on the same screen with no feedback | Fail | Medium | Create a new one time task
TC29 | View shared public task from another user | Another user has shared a public task with current user | 1.Log in the app as the current user 2.Go to notifications or shared tasks section 3.Locate the shared public task |  | The public task shared by another user should be visible with full details | Shared task appeared correctly in notifications and task list | Pass | Medium | Shared public task
TC30 | Fail to like public task when not logged in | user is logged out | 1.Open the app without logging in 2.Navigate to a public task 3.Try to click like button |  | App Should Prompt the user to log in | Like is registered without login | Fail | Low | Like Public Task
TC31 | Create Yearly task with valid data | User is on task creation screen | 1.Click on “create new task” 2.Select “repeatable task” 3.choose “ yearly” 4.enter title “annual report” 5.enter repeat value 3 6.click save | Title: annual report Repeat:3 | Yearly task should be created successfully and shown on the dashboard | Task is saved, but appears as “Monthly” on dashboard | Fail | High | Create a New Yearly Task
TC32 | Upload valid profile image successfully | User is logged in and on account settings page | 1. Click on “Edit Profile” 2. Click on “Upload Image” 3. Select valid image file (e.g., profile.jpg, size < 2MB) 4. Click "Save" | File: profile.jpg | Profile image should be updated and displayed immediately across the app | App crashes immediately | Fail | Medium | Change Account Image
TC33 | Logout from account and restrict access to private pages | User is logged in | 1. Click on the "Settings" or profile menu 2. Click "Log Out" 3. Confirm logout if prompted 4. Try to access dashboard or task list page via browser history |  | User should be logged out, redirected to login page, and unable to access private pages | User logged out and redirected to login page; private pages inaccessible via back button. | Pass | High | Log Out
TC34 | User can submit one-time task without selecting a date | User is on task creation screen | 1. Go to create task 2.Select “One-time Task” 3.Enter a valid title 4.Leave the date field empty 5.Click Submit |  | Validation error should appear ("Date is required") | Task is created and saved with empty date | Fail | High